## Group member 1
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Kenneth Nguyen
Deadline: |  | 2020-05-10 |  | Date:
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Department Table | 2020-04-30 | 2020-05-04
100% | WorkFlowStepTableRowCount Stored Procedure | 2020-04-30 | 2020-05-04
100% | Time Table | 2020-04-30 | 2020-05-04 | 2020-05-09
100% | BuildingAndRoom Table | 2020-05-04 | 2020-05-06
100% | Truncate tables Stored Procedure | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09
100% | JDBC Recording | 2020-05-09 | 2020-05-10

## Group member 2
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Brian Aguilar
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Instructor that can work in more than 1 department Table | 2020-04-30 | 2020-05-04 | 2020-05-07
100% | Instructor Table | 2020-04-30 | 2020-05-04 | 2020-05-07
100% | Create Foreign Keys Stored Procedure | 2020-05-04 | 2020-05-06 | 2020-05-07
100% | Query: How many instructors are in each department? | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09

## Group member 3
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Tristen Aguilar
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Course Table | 2020-04-30 | 2020-05-04 | 2020-05-08
100% | Drop Foreign Keys Stored Procedure | 2020-05-04 | 2020-05-06
100% | Query: Create custom query | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09

## Group member 4
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Minjung Chung
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Class Table | 2020-04-30 | 2020-05-04 | 2020-05-06
100% | Query: Create custom query | 2020-05-04 | 2020-05-06
100% | Query: Create custom query | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09

## Group member 5
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Jordon Johnson
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Building Location Table | 2020-04-30 | 2020-05-04 | 2020-05-08
100% | Process.usp_TrackWorkFlowStep Stored Procedure | 2020-05-04 | 2020-05-07
100% | Query: How many classes that are being taught that semseter grouped by course and aggregating the total enrollement, total class limit and the percentage of enrollment | 2020-05-04 | 2020-05-07
100% | Power Point slides | 2020-05-07 | 2020-05-09
100% | Recordings | 2020-05-08 | 2020-05-09

## Group member 6
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Anthony Ramnarain
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Process.WorkFlowStep Table | 2020-04-30 | 2020-05-04
100% | Room Location Table | 2020-05-04 | 2020-05-06
100% | Query: Show all instructors who are teaching in classes in multiple departments | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09

## Group member 7
To-do list
To be completed by: |  | 2020-05-10 |  | Name: Aliem Noor
Deadline: |  | 2020-05-10 |  | Date
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Mode of Instruction Table | 2020-04-30 | 2020-05-04 | 2020-05-06
100% | Create a single stored procedure that can load all of the production tables on demand using the FileUpload tables | 2020-05-04 | 2020-05-06
100% | Power Point slides | 2020-05-06 | 2020-05-07
100% | Recordings | 2020-05-07 | 2020-05-09
100% | JDBC | 2020-05-07 | 2020-05-09