## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Day Highlight: | 30 |  |  | Plan Duration | [5 empty] | Actual Start |  |  | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | DAYS
[6 empty] | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
WorkFlowStepTableRowCount Stored Procedure | 30 | 5 | 1 | 2 | 100%
Department Table | 30 | 5 | 2 | 3 | 100%
Time Table | 30 | 5 | 8 | 2 | 100%
BuildingAndRoom Table | 4 | 3 | 4 | 3 | 100%
Truncate tables Stored Procedure | 4 | 3 | 4 | 2 | 100%
Instructor that can work in more than 1 department Table | 30 | 6 | 7 | 1 | 100%
Instructor Table | 30 | 6 | 7 | 1 | 100%
Create Foreign Keys Stored Procedure | 4 | 3 | 7 | 1 | 100%
Query: How many instructors are in each department? | 4 | 3 | 4 | 1 | 100%
Course Table | 30 | 6 | 7 | 2 | 100%
Drop Foreign Keys Stored Procedure | 4 | 3 | 4 | 2 | 100%
Query: Create query (Tristen) | 4 | 3 | 4 | 3 | 100%
Class Table | 30 | 6 | 5 | 2 | 100%
Query: Create query (Minjung) | 4 | 3 | 4 | 2 | 100%
Query: Create query (Minjung) | 4 | 3 | 4 | 3 | 100%
Building Location Table | 30 | 6 | 7 | 2 | 100%
Process.usp_TrackWorkFlowStep Stored Procedure | 4 | 4 | 7 | 1 | 100%
Aggregate Total Query | 4 | 4 | 7 | 1 | 100%
WorkFlowSteps Table | 30 | 4 | 4 | 1 | 100%
RoomLocation Table | 4 | 3 | 4 | 3 | 100%
Query: Show all instructors who are teaching classes in multiple departments | 4 | 3 | 7 | 3 | 100%
Mode Of Instruction Table | 30 | 6 | 5 | 2 | 100%
BuildQueensCollegeScheduleSpring2019Database Stored Procedure | 4 | 3 | 5 | 1 | 100%